## Checklist
PCB Design Checklist by Kleber Reis Gouveia Júnior
Project: Interstage Interface Panels for FloripaSat-2 |  |  | Revision: | 1.0
Variant: Semi USB - "IIP_RBF" Board Nº2 |  |  | Date: | 2020-07-11 22:53
1. | Schematic
Description |  | OK | NOK | N/A | Comments
1.1 | 0R resistor to isolate power supplies. |  |  | X | Powered from Texas Instruments Debbuger Tool (MSP-FET)
1.2 | Test points (power supplies, control and status signals, ...). | X |  |  | Approved
1.3 | Power indicator (LED). |  |  | X | Built in MSP-FET
1.4 | Initial state of control signals. |  |  | X | No IC used in design
1.5 | Components power supplies (dual supply, voltage level). |  |  | X | Power provided from debugger
1.6 | Components polarity. |  |  | X | No polarity components
1.7 | Electrical junctions. | X
1.8 | Are there tatalum capacitors? Is it necessary? |  |  | X
1.9 | RC circuit (10k - 100nF) o uC RESET pin. |  |  | X | No IC
1.10 | uC programming/debug connector signals. | X
1.11 | Decoupling capacitors (10nF/100nF) on power supllies outputs. |  |  | X
1.12 | Decoupling capacitors (100nF) in power pins. |  |  | X
1.13 | Ferrite bead and decoupling capacitors in input signals from cables. |  |  | X
1.14 | Differential pair rules. |  |  | X | No high speed design
1.15 | Added template for all schematic sheets | X
1.16 | ESD, EFT, Surge Protection |  |  | X | Not needed for this specific board
1.17 | Recompile project (C+R). | X
1.18 | Add Port Cross Reference (R+P+D). |  |  | X | Simple PCB design (1 sheet)
2. | Layout
Description |  | OK | NOK | N/A | Comments
2.1 | Run DRC (T+D+R). |  | X |  | Needing more revision
2.2 | Holes diameters (>=0,3mm). | X
2.3 | Soldermask on thermal pads. |  |  | X | Direct contact opted in power and GND nets
2.4 | Footprints - holes | X
2.5 | Footprints - dimensions (possible mirroring) | X
2.6 | Pin 1 indication, component polarity indicator. | X
2.7 | Compatibility between schematic models and pcb models. | X
2.8 | Track width | X |  |  | 0.508 mm to power nets and 0.254 mm to signals
2.9 | Power lines |  |  | X | Used polygons for power nets
2.10 | Clearance between silk, silk to role and silk to silk. | X
2.11 | uC programming connector position. | X
2.12 | PCB stackup. | X |  |  | 2 layer 1,6 mm thick
2.13 | PCB zoning. |  |  | X
2.14 | Copper tickness | X |  |  | Standard 1 oz
2.15 | Tracks with controlled impedance. |  |  | X
2.16 | Heavy/Tall component on bottom layer. |  |  | X | Heavy/Taller components must be on top layer for AIT reasons
2.17 | Acute angle on tracks. | X
2.18 | Decoupling capacitors positioning. |  |  | X
2.19 | Company Logo. | X |  |  | Needs revision
2.20 | PCB code and revision | X
2.21 | PCB Document mechanical layers configuration and names | X
2.22 | Layers markers. |  |  | X | Only 2 layers
2.23 | Stackup table. | X
2.24 | Drill table. | X
2.25 | Silk RoHS, PB Free and ESD |  |  | X
2.26 | Components fiducials. | X
2.27 | PCB fiducials. | X
2.28 | Mechanical holes. | X
2.29 | 3D .step bodies. | X
2.30 | Connectors counter parts assembly. | X
2.31 | Internal planes connections. |  |  | X
2.32 | Thermal reliefs between pads and poligons. |  |  | X
2.33 | Via stitching. |  |  | X
2.34 | Via tenting. | X
2.35 | Test points. | X
2.36 | Teadrops. | X
2.37 | Make PCB Re-annotate and SCH Back annotate. |  |  | X | Few components to be an advantage
2.38 | Check the manufacture capabilities for the targeted PBC factory | X |  |  | Considering manufacture in JLCPCB
3. | Documentation
Description |  | OK | NOK | N/A | Comments
3.1 | .OutJob file configuration. | X
3.2 | BOM.xls | X
3.3 | QUOTE.xls |  |  | X
3.4 | SCH.pdf | X
3.5 | GERBERS.zip | X
3.6 | NC Drill files.zip | X
3.7 | Pick and Place files.zip | X
3.8 | ODB++.zip | X
3.9 | Special Fabrication Instruction.pdf |  |  | X
3.10 | User's guide manual (PDF) |  | X |  | Under development
4. | Technical Responsibles
Name |  | Role |  |  | Signature
4.1 | Yan Castro de Azeredo | Drawing
4.2 | Gabriel Mariano Marcelino | Review and support
4.3 | André Martins de Pio Mattos | Review and support
4.4 | Edemar Morsch Filho | Mechanical validadtion